## Slide 1
H
HealthSphere AI
Production Readiness Sprint
Feature-complete MVP → Production-hardened, scalable, compliant → Real users
4-5 Day Sprint
16 Slide Deck
Go / No-Go Plan
Zero-dependency Node backend · Vanilla JS SPA · Supabase Postgres · Free-tier cloud storage
HealthSphere AI · Production Readiness Sprint
1 / 17

## Slide 2
Agenda
HealthSphere AI · Production Readiness Sprint
2 / 17
01
Architecture Overview
What we have today
02
Family Tree Hierarchy
4-generation health tree & condition inheritance
03
Critical Gaps
Security · Scale · Compliance · Features
04
Day-by-Day Plan
4–5 day execution breakdown
05
Database Migration
JSON blob → relational Postgres (30 tables)
06
Security Hardening
Auth · Headers · MFA · CSRF · Rate Limits
07
Observability
Logs · Metrics · Alerts · Error Tracking
08
Launch + Roadmap
Go/No-Go criteria · Week 2 → Quarter 1

## Slide 3
Architecture Overview
Current Stack — Feature-Complete MVP
HealthSphere AI · Production Readiness Sprint
3 / 17
Layer | Technology | Status
Backend | Node.js 18+ (ESM), zero framework HTTP server | Complete
API | Custom REST router + hash-based SPA | Complete
Database | JSON file OR Supabase jsonb (single row) | MVP Only
File Storage | 4-tier: Supabase / Cloudinary / DB-embed / Local | Working
Auth | scrypt + HttpOnly cookies, 7-day sessions | Working
Frontend | Vanilla JS SPA, hash router, Service Worker | Complete
AI / Insights | Rule-based extraction, trends, risk signals | Complete
Multi-role | Patient / Doctor / Store Owner / Admin | Complete
Deployment | Docker + Vercel + Railway-ready | Ready
✓
Zero Dependencies
No Express, no React, no ORM
Runs anywhere: Vercel, Docker, VPS
⚡
Explainable AI
Rules engine shows WHY each signal
No hallucination risk, auditable
☁
Offline-First
Service Worker caching
Works on flaky connections

## Slide 4
How It Works Today
Request Flow & Data Path
HealthSphere AI · Production Readiness Sprint
4 / 17
Browser
Vanilla JS SPA
Hash router
Service Worker
Fetch API (cookies)
Node.js Server
server.js (http)
lib/api.js (router)
Security headers
Static file serving
Storage
Supabase Postgres (jsonb)
OR local data/db.json
Supabase Storage (files)
OR Cloudinary
Auth Module
scrypt password hash
Session tokens
Rate limiting
Audit logging
Extraction Engine
PDF/TXT parsing
38 lab analytes
Reference ranges
Plain-language explain
Trend Engine
Linear regression
Anomaly detection
Direction analysis
Staleness alerts
Risk Engine
Rule-based signals
Severity: attention/watch/info
Explainability (why)
Safety sanitize layer
Family Tree Hierarchy
4-generation SVG graph
Grandparents → Children
Condition inheritance map
Feeds risk + screening
Patient Portal
Reports, Trends, Insights, Care
Doctor Portal
Verification, Consults, Schedule
Store Portal
Inventory, Orders, Dashboard
Admin Panel
Users, Audit, System Info

## Slide 5
Family Tree & Health History Hierarchy
4-generation SVG graph · powers risk signals + screening checklists
HealthSphere AI · Production Readiness Sprint
5 / 17
RM
Ramesh Mehta
Grandfather · ~84
?
Unknown
Grandmother
?
Unknown
Grandmother
?
Unknown
Grandfather
SM
Suresh Mehta
Father · 61
NM
Nirmala Mehta
Mother · 58
AM
Arjun Mehta
You · 38
PS
Priya Shah
Sister · 33
MM
Mahesh Mehta
Uncle · 57
?
Child
No data
?
Child
No data
Grandparents (Gen 1)
Parents (Gen 2)
You (Gen 3)
Siblings (Gen 3)
Children (Gen 4)
Conditions on tree:
RM (Grandfather): Type 2 Diabetes, Hypertension
SM (Father): Hypertension, High Cholesterol
NM (Mother): Hypothyroidism
MM (Uncle): Type 2 Diabetes
You (Arjun): Prehypertension
How Family Tree Feeds the System
Risk Engine (rules.js)
Family history of diabetes/cardio/cancer triggers risk signals with severity
Screening Checklist
recommend.js: cancer history, cardiovascular family → screening items
Insights Aggregation
insights.js: family conditions mapped to normalized risk categories
AI Assistant
assistant.js: answers questions about family health history

## Slide 6
Critical Gaps for Production
What blocks real-user launch
HealthSphere AI · Production Readiness Sprint
6 / 17
CRITICAL — Blocks Launch
Gap | Impact | Effort
No relational DB (JSON writes won’t scale) | Data corruption, no concurrency | 1 day
No HTTPS enforcement (Secure cookies missing) | Session hijacking, MITM risk | 2 hrs
No password reset flow | Users locked out permanently | 4 hrs
No email notifications (reminders, SOS, consults) | Core features silent | 4 hrs
No observability (logs, metrics, alerts) | Blind in production | 1 day
HIGH — Degrades Experience
Gap | Impact | Effort
No MFA (multi-factor authentication) | Credential stuffing risk | 4 hrs
No CSRF protection on mutating endpoints | State-changing attacks | 2 hrs
No family sharing (invite links) | Major user value missing | 4 hrs
No load testing | Unknown capacity at scale | 2 hrs
No legal docs (Privacy, Terms, DPA) | Compliance risk | 2 hrs

## Slide 7
Day 1 — Infrastructure & Database Migration
6–8 hours · Deliverable: staging URL with migrated data
HealthSphere AI · Production Readiness Sprint
7 / 17
MORNING (3–4 hrs)
☐
Provision Supabase project (Postgres + Storage)
☐
Create Cloudinary account (signed uploads, free tier)
☐
Design Postgres schema — 30 relational tables
☐
Write migration script: JSON → relational tables
☐
Test migration locally with existing seed data
☐
Verify: all data queryable, indexes in place
AFTERNOON (3–4 hrs)
☐
Deploy to Railway / Render (persistent VM)
☐
Configure custom domain + TLS (Caddy auto-HTTPS)
☐
Set ALL production environment variables
☐
Enable Supabase PITR (point-in-time recovery)
☐
Verify /api/health works end-to-end
☐
Test file upload → Supabase Storage → download
Key files to create:
scripts/migrate-to-postgres.mjs · backend/lib/db.js (rewrite) · backend/lib/schema.sql

## Slide 8
Day 2 — Auth Hardening & Email
6–8 hours · Deliverable: password reset + emails working
HealthSphere AI · Production Readiness Sprint
8 / 17
SECURITY (3–4 hrs)
☐
Add "Secure" cookie flag (auto on HTTPS)
☐
Add HSTS header: max-age=31536000; preload
☐
Implement CSRF tokens (double-submit pattern)
☐
Rate limit: 5/min auth, 30/min uploads
☐
Run npm audit + fix vulnerabilities
☐
OWASP ZAP baseline scan
EMAIL (3–4 hrs)
☐
Create Resend account (3k emails/mo free)
☐
POST /api/auth/forgot-password — signed JWT token
☐
POST /api/auth/reset-password — validates, updates hash
☐
Email templates: reset, welcome, consult, reminder
☐
SOS alert email to primary contact
☐
Test full reset flow + delivery to inbox
New env vars:
RESEND_API_KEY · EMAIL_FROM · APP_URL · CSRF_SECRET

## Slide 9
Day 3 — MFA + Family Sharing + Observability
6–8 hours · Deliverable: MFA, invites, logs/metrics visible
HealthSphere AI · Production Readiness Sprint
9 / 17
MFA (TOTP)
☐
Add otplib for TOTP generation
☐
POST /api/auth/mfa/enable — QR + backup codes
☐
POST /api/auth/mfa/verify — enable on account
☐
POST /api/auth/mfa/disable — requires TOTP
☐
Modify loginUser: require TOTP if enabled
☐
Settings UI: show QR, manage backup codes
Family Sharing
☐
POST /api/family/invite — signed token (7d)
☐
Email invite link to family member
☐
GET /api/family/accept/:token — link accounts
☐
Consent flags: viewer / editor roles
☐
UI: Invite button in views-family.js
☐
Accept page: onboarding + consent flow
Observability
☐
pino structured logging (req ID, latency)
☐
Ship logs to Better Stack (free tier)
☐
Sentry error tracking (free tier)
☐
Custom metrics: users, uploads, consults
☐
UptimeRobot: /api/health every 60s
☐
Alert: 3 consecutive failures → Slack
Env: SENTRY_DSN · BETTER_STACK_SOURCE_TOKEN · BETTER_STACK_INGEST_HOST · UPTIMEROBOT_API_KEY

## Slide 10
Day 4 — Polish, Load Test & Legal
6–8 hours · Deliverable: load test pass, legal docs live
HealthSphere AI · Production Readiness Sprint
10 / 17
QUALITY (3–4 hrs)
☐
axe-core accessibility audit → WCAG 2.1 AA
☐
Onboarding flow: welcome → profile → report
☐
Mobile responsiveness fixes (iOS Safari, Android)
☐
Service Worker update strategy (versioned cache)
☐
k6 load test: 100 VUs, p95 < 500ms, err < 0.1%
☐
Add DB indexes + connection pooling if needed
LEGAL & COMPLIANCE
☐
Privacy Policy (termly.io or manual draft)
☐
Terms of Service
☐
GDPR: DPA with Supabase + Cloudinary
☐
Data Protection Impact Assessment (DPIA)
☐
Medical disclaimer review (footer)
☐
Incident response runbook (1-pager)
Run load test:
k6 run scripts/load-test.js -e BASE_URL=https://staging.healthsphere.ai

## Slide 11
Day 5 — Buffer + Launch
4–6 hours · Deliverable: LIVE FOR REAL USERS
HealthSphere AI · Production Readiness Sprint
11 / 17
MORNING (2–3 hrs)
☐
GitHub Actions CI/CD: lint → test → deploy
☐
Playwright smoke tests: auth, upload, consult, SOS
☐
Rollback plan documented
☐
— Supabase PITR + instant rollback
☐
Pre-launch smoke test on staging
☐
Team on-call roster confirmed
AFTERNOON (2–3 hrs)
☐
PRODUCTION DEPLOY -> LIVE
☐
Post-deploy verification checklist
☐
Monitor for 2 hours (Sentry, Better Stack)
☐
DNS switch + SSL verification (A+ grade)
☐
Smoke test all roles: patient, doctor, store
☐
Hand-off doc: runbooks, contacts, escalation
Go / No-Go Criteria
Uptime 99.9% · API p95 < 500ms · Error rate < 0.1% · 0 OWASP High/Critical · 0 axe violations · Load test pass

## Slide 12
Database Migration: JSON → Relational Postgres
30 tables, indexed queries, transaction-safe
HealthSphere AI · Production Readiness Sprint
12 / 17
BEFORE: JSON blob
Single jsonb row in Supabase. Every write = full state rewrite. No indexes, no concurrent access, no query planner.
AFTER: 30 relational tables
Proper schema, indexed queries, concurrent writes, query planner optimization, ACID transactions.
Core Users (4)
users, sessions, profiles, family_members
Health Data (4)
reports, metrics, lifestyle_logs, plans
Care Team (4)
doctors, contacts, reminders, sos_alerts
Settings (3)
settings, audit_logs, feedback
Multi-role (3)
doctor_accounts, store_owner_accounts, stores
Consultations (3)
consult_tickets, consult_appointments, consult_messages
Invites (1)
family_invites
idx_metrics(user_id,key,date) · idx_audit(user_id,ts) · idx_reports(user_id,uploaded_at)

## Slide 13
Security Hardening
Defense-in-depth for health data
HealthSphere AI · Production Readiness Sprint
13 / 17
Transport & Headers
Strict-Transport-Security: max-age=31536000; preload
Content-Security-Policy: default-src 'self' ...
X-Content-Type-Options: nosniff
X-Frame-Options: DENY
Referrer-Policy: strict-origin-when-cross-origin
Cookies: HttpOnly + Secure + SameSite=Lax
Auth Upgrades
Password Reset: Signed JWT, 15-min expiry, email link
MFA (TOTP): otplib, QR code, 8 backup codes
Session Security: 7-day expiry, revoke on password change
Rate Limiting: 5/min auth, 30/min uploads, 10/min feedback
CSRF Tokens: Double-submit cookie pattern
Audit Logging: Every auth action recorded
Layer 1: Transport
TLS 1.3, HSTS, Secure cookies
Layer 2: Input
Validation, sanitization, CSRF tokens
Layer 3: Auth
scrypt, MFA, rate limiting, session mgmt
Layer 4: Authorization
Role-based access, admin-only checks
Layer 5: Data
Encryption at rest, PII minimization, audit
Layer 6: Output
CSP headers, XSS prevention, prompt-injection guard

## Slide 14
Observability Stack
Logs, metrics, error tracking, uptime
HealthSphere AI · Production Readiness Sprint
14 / 17
Logging
pino → Better Stack
• Structured JSON logs
• Request ID propagation
• User context (no PII)
• Latency per endpoint
• Free tier: 1GB/mo
Error Tracking
Sentry (free tier)
• Auto-capture exceptions
• Source maps in CI
• Alert on new error types
• Breadcrumb trail
• Free tier: 5K errors/mo
Metrics
Custom + Better Stack
• api_latency_p95 < 500ms
• api_error_rate < 0.1%
• active_users_24h
• report_uploads_total
• consult_volume
Uptime
UptimeRobot (free tier)
• /api/health every 60s
• Alert: 3 failures → Slack
• Status page for users
• SSL expiry monitoring
• 50 monitors free
Sample structured log:
{"level":"info","reqId":"abc123","userId":"usr_xyz","method":"POST","path":"/api/reports","status":200,"latencyMs":142}

## Slide 15
Launch Checklist
Go / No-Go criteria before production deploy
HealthSphere AI · Production Readiness Sprint
15 / 17
☑
Unit tests pass (npm test)
☑
Migration verified — all data queryable
☑
File upload: PDF → Cloud → download works
☑
Auth flow: register → login → MFA → reset → logout
☑
Email delivery confirmed (reset, welcome, SOS)
☑
Family invite link works and expires correctly
☑
Admin panel: users, drill-down, audit, delete
☑
Doctor + Store portals functional
☑
Accessibility: 0 WCAG 2.1 AA violations
☑
Load test: 100 VUs, p95 < 500ms, error < 0.1%
☑
Security scan: 0 OWASP High/Critical
☑
SSL Labs grade A+
☑
All env vars set (no .env files in prod)
☑
Supabase PITR enabled + restore tested
☑
Better Stack alerts configured
☑
Sentry error rate < 0.1%
☑
UptimeRobot monitor active
☑
Rollback plan tested
☑
Legal pages live (/privacy, /terms)
☑
Team on-call for 4 hours post-launch
✓ ALL CHECKS PASSED — READY FOR PRODUCTION DEPLOY

## Slide 16
Post-Launch Roadmap
Week 2 → Quarter 1
HealthSphere AI · Production Readiness Sprint
16 / 17
1
Week 1
Stabilize
• Monitor, fix bugs, gather feedback
• User feedback collection (in-app + email)
• Performance optimization from real traffic
• Bug fixes from launch week
2
Week 2-4
Core Enhancements
• FHIR export for clinical interoperability
• Mobile app via Capacitor wrapper (iOS/Android)
• Doctor portal: schedule, prescriptions
• Pharmacy integration (eRx standards)
3
Month 2-3
Scale & Differentiate
• Insurance claims helper
• AI insights v2 (fine-tuned on data)
• Multi-language (i18next)
• Enterprise: SSO, audit API, white-label
4
Quarter 2+
Long-term
• Wearable integrations (Fitbit, Apple Health)
• Telemedicine video calls (WebRTC)
• Insurance claim automation
• Regional expansion (multi-country)

## Slide 17
Summary & Next Steps
4-5 Days
From MVP to production-ready
30 Tables
JSON blob → relational Postgres
100 VUs
Load tested p95 < 500ms
99.9%
Target uptime with monitoring
Decisions Needed Before Day 1
1. Hosting target: Railway/Render (VM) vs Vercel (serverless)?
2. Email provider: Resend (recommended) vs SendGrid vs AWS SES?
3. MFA optional for patients, required for admins?
4. Family sharing default role: Viewer or Editor?
START DAY 1 NOW
Provision Supabase · Run migration script · Deploy to staging · Launch in 5 days
HealthSphere AI · Production Readiness Sprint
16 / 17